## F_V_1.0
Formsz Build Release Management
| Product | Formsz
| Build Version | F_V_1.0
| Release Date | 2016-07-06
Mobile
S.No | Feature | Developed By | Status | Remarks
1 | User Login in Online | Ajay | Completed | NA
2 | Online Forms list | Roja | Completed | NA
3 | Online forms View & Sumbit | Roja | Completed | NA
4 | Online forms Download | Ajay / Roja | Completed | NA
5 | Online forms Info | Ajay / Roja | Completed | NA
6 | Search functionality | Roja | Completed | NA
7 | Mobile designs | Sairam | In-progress | Need to change Logo and splash screen
Web
S.No | Feature | Developed By | Status | Remarks
1 | Root / Admin Login & Logout | Venki / Phani | Completed | NA
2 | Portal UI Template | Phani | Completed | Need to change the UI
3 | Admin Creation | Venki / Uma /Phani | Completed | Change the UI & Mandatory fields
4 | Edit & Update Admin details | Uma | Completed | NA
5 | Delete Admin | Uma | Completed | NA
6 | User group Creation | Venki / Uma /Phani | Completed | Changes are required like email, Phone no
7 | Edit User group | Venki / Uma /Phani | Completed | Changes required
8 | Delete User group | Venki / Uma | Completed | NA
9 | User Creation | Venki / Uma | In-progress | NA
10 | Edit User | Venki / Uma /Phani | Completed | NA
11 | Delete User | Venki / Uma | Completed | NA
12 | Form Creation | Venki / Phani | In-progress | Add new widgets and validations
13 | View / Edit & Update Form | Venki / Uma | In-progress | Changes are required
14 | Get records in Tabular view | Venki / Phani / Uma | In-progress | Add Is-primary keys
15 | Delete form | Venki / Uma | Completed | NA
16 | Services for all modules | Bhanu | In-progress | NA

## F_V_2.0
Formsz Build Release Management
| Product | Formsz
| Build Version | F_V_2.0
| Release Date | 19/7/2016
Mobile
S.No | Feature | Developed By | Status | Remarks
1 | Offline User Login, Logout | Ajay | Completed | N/A
2 | Offline form saving | Roja | Completed | N/A
3 | Offline forms history, Edit & delete records | Roja | Completed | N/A
4 | switching online to offline toggle | Ajay | Completed | Toggle button complete, functionality is progress
5 | Online forms History | Roja | Completed | N/A
6 | In-progress (Offline) records history | Roja | Completed | N/A
7 | Offline forms edit and Save | Roja | Completed | N/A
8 | Sync and delete multiple records | Roja | Completed | N/A
9 | Show re-assign records | Roja | Completed | N/A
10 | Edit and sync re-assign records | Roja | Completed | N/A
11 | Mobile designs | Sairam | Completed | N/A
Web
S.No | Feature | Developed By | Status | Remarks
1 | Updates in Admin and User creation | Venkatesh/Uma | Completed | N/A
2 | Form and Template creation | Venkatesh/Uma | Completed | N/A
3 | New widgets and validations in Form creation | Venkatesh/Uma | Completed | N/A
4 | Form Edit, Update and Copy | Venkatesh/Phani | Completed | N/A
5 | Get records in Tabular& Grid views | Venkatesh/Phani | Completed | N/A
6 | Export records to mail & Excel sheet | Phani | Completed | N/A
7 | Print individual record in pdf format | Phani | Completed | N/A
8 | Re-assign records with comments | Uma/Phani | Completed | N/A
9 | Form creation with selected users | Venkatesh | Completed | N/A
10 | Light view login | Venkatesh | Completed | N/A
11 | Web user login | Venkatesh | Completed | N/A

## F_V_3.0
Formsz Build Release Management
| Product | Formsz
| Build Version | F_V_3.0
Mobile
S.No | Feature | Developed By | Status | Remarks
1 | Show assigned Tasks | Roja | Completed | NA
2 | Download tasks | Roja | Completed | NA
3 | Showing task description and forms | Roja | Completed | Functionality need to be change due to UI changes
4 | Show re-assigned records & comments | Roja | Completed | NA
5 | Download re-assign records | Roja | Completed | NA
6 | Show downloaded forms, tasks and re-assign records in downloads tab | Roja | Inprogress | Dependency with designs
7 | Edit & Update forms and Tasks in offline | Roja | Completed | NA
8 | Save and Sync tasks in online | Roja | Completed | NA
9 | Change User password | Roja | Completed | NA
10 | Mobile Forgot password | Roja | Completed | NA
11 | Showing Pre-populated data records in assigned task | Roja | In-progress | High priority
12 | Showing records on map | Ajay | In-progress | High priority
13 | Calculated fields | Ajay | On hold | Pending on Client side
14 | Network Online-Offline toggle | Roja/Ajay | Completed | NA
15 | About Us | Roja/Ajay | Not yet started
16 | Show alert notifications | Roja/Ajay | Not yet started
17 | Mobile designs | Sairam | In-progress
Web
S.No | Feature | Developed By | Status | Remarks
1 | Create category for templates in Root account | Venkatesh/Phani | Completed | NA
2 | Create category for forms in Admin account | Venkatesh/Phani | Completed | NA
3 | Edit & Update and Delete category | Venkatesh/Phani | Completed | NA
4 | Form types Public,Private, General | Venkatesh/Uma | Completed | NA
5 | Task creation | Venkatesh | Completed | NA
6 | Edit & Update task | Venkatesh | Completed | NA
7 | Download form in excel format | Venkatesh | Completed | NA
8 | Create pre-populated datasheet and convert in JSON format | Venkatesh | Completed | NA
9 | Attach Pre-populated datasheet for task | Venkatesh/Uma | Completed | NA
10 | Show submitted records in Tabular view | Venkatesh/Uma | Inprogress | For forms it was done, but for tasks facing some challenges
11 | Get records in Grid view | Venkatesh/Uma | In-progress | Need to do some changes for pdf format and Mailing services
12 | Record re-assign to selected user with comments | Uma | Completed | NA
13 | View comments history for re-assign records | Venkatesh | Completed | NA
14 | Export records in csv format, Pdf and mail | Uma | Completed | NA
15 | Create users by reading excel sheet | Uma | Completed | NA
16 | Web user form fill and submit | Uma | Completed | NA
17 | Web user form submitted history | Uma | Completed | NA
18 | License transactions | Bhanu/Venkatesh | Completed | NA
19 | Map component enable or disable for pre-poulated datasheet | Uma | Completed | NA
20 | Show assigned tasks for web user | Uma | In-progress | Need to do some changes to submit the task assigned forms
21 | Calculated widget | Venkatesh | In-progress
22 | Show pre-populated data records for web user | Uma | In-progress
23 | Provide fields info in pre-populated dat sheet | Uma | In-progress
24 | All services | Bhanu/Divya | In-progress