## Portal_Bugs
Formsz_Portal bugs
Version -V3.0
S.No | Test object | Test description | Severity | Dev Status | Dev Remarks | QA Status
F_P_1 | Form widgets -> Text box field | In text box set properties drop down is not static | High
F_P_2 | Admin edit & Update | Only for image changes- update button is not enabled | Medium
F_P_3 | Admin edit & Update | Corresponding user group shows as free i.e not assigned, and for that same user group new admin created successful and both admins can login with same group name | High
F_P_4 | Delete Admin | Spell check in admin "Deletion" cancel pop up | Low
F_P_5 | Create category | Spell check in category "created" successfully | Low
F_P_6 | Calculation field preview | In form preview each calculation field displays twice | High
F_P_7 | Template creation | Off -side click to close current pop up in template creation, Form creation | Low
F_P_8 | Template creation | After adding fields, click on Create form- it shows "Submit form" Change it as "create Template" | Low
F_P_9 | Admin creation | No validation error text for phone num field in admin creation | Low
F_P_10 | Tasks in admin | For no tasks it doesn't show count(0 out of 0 records) & "no results found" message and Task icon should be unique in menu and main page. Check lable name "TASKS" at header | Low
F_P_11 | Users in admin | Users icon should be unique | Low
F_P_12 | Search box in category | Spell check of "category" in search box | Low
F_P_13 | Form creation-> Select type | Remove search icon in select form type and form category in Form creation | Medium
F_P_14 | Formsz-> Filter category | Filter with category- Category button enable / disable, Filter components swapping | Medium
F_P_15 | Create category | Black transparency in create category field | Low
F_P_16 | Form creation pop up | No unique representation icons for GO and Cancel buttons in form creation pop up | Low
F_P_17 | Textbox field | No unique representation icons for Save and Cancel buttons in Text box field | Low
F_P_18 | Textbox widget-> number field | For number field min & max validations- it shows minimum is not exceed max when I gave length 10 for both fields. Color should not be changed for Yes or No options, and Save button changes for selection of Yes or No | Medium
F_P_19 | Rating field | Default value for rating field is not updated properly,default label names needs to be correction(poor'P', Excellent) | Medium
F_P_20 | Form preview->Barcode | In form preview Barcode field type is not display | Medium
F_P_21 | Get records tabular view | No need to display Create new form button when user is in records page | Medium
F_P_22 | Task creation | Button icon need to maintain unique, and description text should be wrapping | Medium
F_P_23 | Task creation | Spell check in task "Created" successfully pop up | Low
F_P_24 | Edit task | Button icons should be unique, and make sure "task name is non editable field" | High
F_P_25 | Task ->Get records | Filter search is not working properly, and filter fields are not clear, fill with previous search data, filter button size needs to be change | Medium
F_P_26 | Task ->Get records | If no results to show, there is no notification message in task level tabular records | Low
F_P_27 | Task page | Search task- mouse hover text need to be changed | Low
F_P_28 | Form creation details page | Private type user selection dropdown is not proper way to close | Medium
F_P_29 | Form widgets | Space between Place Holder | Low
F_P_30 | Camera widget->Image properties | In image properties- Field validation error message is displayed when mouse hover on Image size field. No need to show error text for image parameter field in image size field, Once save properties and again open- parameter field is in enable state | Medium
F_P_31 | Calendar widget | Calendar properties min & max date fields validation need to be change | Medium
F_P_32 | Widget label names | For textbox(Text,Email,Num), location, Signature fields label names are mis-aligned | Low
F_P_33 | Calculation field | Calc field-Error validation messages are not cleared even creating the formula | High
F_P_34 | Group & Section widgets | For Group and Section fields-place holder text is not in appropriate way | Low
F_P_35 | Tabular view | Spell check of 'Tabular view' in records table | Low
F_P_36 | Tabular view | In Table header re-assign records STATUS lable needs to be change. | Low
F_P_37 | Tabular view | Spell check of Re-assign records in records table | Low
F_P_38 | Tabular view | In tabular no minimum field length to view the data | Medium
F_P_39 | Tabular view | Signature field is not updated. | Medium
F_P_40 | Tabular view | Records submitted date & time is incorrect in grid view. | Medium
F_P_41 | Records export | Spell check of 'Report' in export data as csv | Low
F_P_42 | Records export | Export pdf is not working properly | High
F_P_43 | Records mail | Records mailing is failed, but for no records mail sent successfully | High
F_P_44 | Tabular view | Field editing in records should not allow | Medium
F_P_45 | Records export | Even though no records, re-assign allows successfully and mail sent, export csv successfully. | High
F_P_46 | Re-assign popup | In re-assign- Select group & choose one text need to be change | Low
F_P_47 | Tabular view-> Filter | In tabular view, previous dates filter results doesn't shows re-assign & assign lables and search fields also disabled | High
F_P_48 | Re-assign records in table | Re-assgin and orginal records updating incorrectly i.e, instead of selected record another record is re-assigned. | High
F_P_49 | Task assigned form delete | Task assigned form deleted successfully. No validations for task assigned form, Records are not updated in table | High
F_P_50 | Tabular view | Images are updated improperly in tabular view. | High
F_P_51 | Tabular view | If form updated , get records table shows reassigned and original status. | Medium
Webuser
F_P_52 | Forms page | Remove select user filter, select category, select form type | Medium
F_P_53 | Form submission | "Submitted" spell check after form submission. | Low
F_P_54 | Records history | submitted records are not updated in table. | Medium
F_P_55 | Forms page | Formsz icon should be unique | Low
F_P_56 | Forms page | Change form edit button to view button | Low
F_P_57 | Form filling | In form,text box and text area fields are display in normal font and remaining fields are in bold font | Medium
F_P_58 | Form filling | Check box displayed at right side of the text, but in preview it displayed left side | Medium
F_P_59 | Form submission | Mandatory' spell check in form submission without enter all fields | Low
F_P_60 | View form | Validation messages are not cleared and dispalyed in remaing forms also | Medium

## Pending functionality
Forms_Portal
S.No | Test object | Test description
F_P_1 | Form creation | when user select new widget- page will scroll to selected widget to set properties
F_P_2 | Form creation | Before submit form creation, all required fields are not updated in choose field
F_P_3 | Pagination | No pagination for Formsz,Category,Tasks pages
F_P_4 | View record | No option for viewing full record.
F_P_5 | Barcode | In csv format Barcode is updated as binary number
F_P_6